## CapacityPlanning
Resource Name | Project/SSCR name | Planned Release month | Project Role | Legato Manager Name | Anthem Manager | Project Model | Planned Hours | Actual Hours | Remaining Hours | Planned Requirements Hours | Planned Requirement Analysis Hours | Actual BRD Hours | Actual BRD Review Hours | Planned Design Hours | Planned Test Design Hours | Actual LOE 90% Hours | Actual TDD Hours | Actual Unit Test Plan Hours | Actual Design Review Hours | Planned Development Hours | Planned Test Data Creation Hours | Actual Coding Hours | Actual Unit Testing Hours | Actual Code UT Review Hours | Actual Code Retro Fit Hours | Actual SIT Test Plan Hours | Actual SIT Preparation Review Hours | Planned SIT Hours | Planned Test Execution Hours | Actual Test Execution Hours | Actual Test Review Hours | Actual Requirement Analysis | Actual Test Design | Actual Test Data Creation | Actual Defect Management | Actual Communication And Status Reporting | Actual Rework | Planned UAT Hours | Test Review Hours | Actual UAT Code Retro Fit Hours | Actual UAT Code Fix Hours | Actual UAT Fix Test Hours | Planned STC Hours | Defect Management Hours | Actual STC Results Review Hours | Actual STC Code Fix Hours | Actual STC Fix Test Hours | Planned Release Hours | Planned Communication and Status Reporting Hours | Actual Release Checklist Hours | Actual Implementation Support Hours | Actual Post Implementation Support Hours | Planned Warranty Support Hours | Planned Rework Hours | Actual Warranty Hours | Actual Adhoc Hours | Actual Adhoc Analysis Hours | Actual Idle Time Hours | Actual PTO Hours | Actual Total Other Hours | Actual Task1 Hours | Task1Comments | Actual Task2 Hours | Task2Comments | Actual Task3 Hours | Task3Comments | Actual Task4 Hours | Task4Comments | Actual Task5 Hours | Task5Comments | Actual Task6 Hours | Task6Comments | Actual Task7 Hours | Task7Comments | Actual Task8 Hours | Task8Comments | Actual Task9 Hours | Task9Comments | Actual Task10 Hours | Task10Comments | Actual Away From Work Hours | AwayFromWorkComments
Gangwar, Kamal [AF40660] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 96 | 125 | -29 | 400 | 0 |  |  | 1000 | 0 |  | 4 |  | 19 | 1500 | 0 | 29 | 19.5 | 33.5 |  | 4.5 | 5 | 250 | 0 |  | 10.5 | [6 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0
Gangwar, Kamal [AF40660] | Others |  | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 83 | 28.5 | July Release STC Validation - [5.00];Ad-Hoc Reporting for CV Online Eligible claims - [4.50];Analysis on region Issue as a part of QRF - [8.00];Aug Release Ad-hoc Item - [11.00] | 25.5 | July Release STC Issue Analysis and Fix - [9.50];July Release STC4 Validations - [5.00];Cotiviti Ad-hoc Reporting items - [4.00];Cotiviti Re-processing Prod Issue - [7.00] | 13 | Ad-Hoc Reporting and Analysis - [8.00];Cotiviti July Release Items Checkout Review - [2.00];Pend Edit Analysis - [3.00] | [14 empty] | 16 | Sick Leave - [8.00];Holiday - [8.00]
Gangwar, Kamal [AF40660] | PV36064 Cotiviti Pre to Post Phase 3 | June 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 52 | 7.5 | 44.5 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 230 | 0 | [6 empty] | 150 | 386 | [8 empty] | 150 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 62 | 0 |  |  | 7.5
Gangwar, Kamal [AF40660] | PV36064_Cotiviti expansion | February 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0
Gangwar, Kamal [AF40660] | PV38761 ClaimXten Expansion | June 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 36 | 0 | 36 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Manohar, Gande [AG34344] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 112 | 152.5 | -40.5 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 | 43 | 65.5 |  |  |  |  | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 | 1 | 3 | 4 | 50 | 0 | 8 |  | 3 | 50 | 0 |  |  | 25
Manohar, Gande [AG34344] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 72 | 40.5 | 31.5 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 11.5 | 16.5 | 9 |  |  |  | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 3.5
Manohar, Gande [AG34344] | PV36064 Cotiviti Pre to Post Phase 3 | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 230 | 0 | [6 empty] | 150 | 386 | [8 empty] | 150 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 62 | 0
Manohar, Gande [AG34344] | PV36064_Cotiviti expansion | February 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0
Manohar, Gande [AG34344] | PV38761 ClaimXten Expansion | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Modepalli, Sateesh [AG63417] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 100 | 102 | -2 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 | 43.5 | 54 | 4.5 |  |  |  | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Modepalli, Sateesh [AG63417] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 84 | 82.5 | 1.5 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 15.5 | 41.5 |  |  |  | 25.5 | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0
Modepalli, Sateesh [AG63417] | Others |  | Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 8 | [20 empty] | 8 | I am in leave - [8.00]
Modepalli, Sateesh [AG63417] | PV38761 ClaimXten Expansion | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Mudumba, Rambabu [AG13560] | Cotiviti E & M Leveling | October 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 500 | 0 |  |  |  |  | 700 | 0 | [6 empty] | 240 | 0 | [8 empty] | 80 | 0 |  |  |  | 80 | 0 |  |  |  | 40 | 0 |  |  |  | 110 | 0
Mudumba, Rambabu [AG13560] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 184 | 160 | 24 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 40 | 80 | 24 |  |  |  | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 16
Mudumba, Rambabu [AG13560] | PV36064 Cotiviti Pre to Post Phase 3 | June 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 230 | 0 | [6 empty] | 150 | 386 | [8 empty] | 150 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 62 | 0
Mudumba, Rambabu [AG13560] | PV36064_Cotiviti expansion | February 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0
Mudumba, Rambabu [AG13560] | SSCR 52416 Cotiviti Ex codes | August 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 20 | 0 |  |  | 0 | 0 |  |  |  |  | 24 | 0 | [6 empty] | 40 | 0 | [8 empty] | 10 | 0 |  |  |  | 10 | 0 |  |  |  | 10 | 0 |  |  |  | 10 | 0
Mudumba, Rambabu [AG13560] | SSCR 52416 Cotiviti Excode 00I87 & 00H74 | January 2020 | Senior Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 24 | -24 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 10 | 0 | 12 | 6 |  |  |  |  | 40 | 0 | [8 empty] | 20 | 0 |  |  |  | 20 | 0 |  |  |  | 25 | 0 |  |  |  | 10 | 0 |  |  | 6
Musuloju, Siddartha [AG63426] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 120 | 109 | 11 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 |  | 41 | 19.5 |  |  |  | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 | 16.5 |  |  | 50 | 0 | 16 |  |  | 50 | 0 |  |  | 16
Musuloju, Siddartha [AG63426] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 56 | 44 | 12 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 16 | 21 |  |  |  |  | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 7
Musuloju, Siddartha [AG63426] | Others |  | Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 8 | [20 empty] | 8 | Was suffering from Health issues. - [8.00]
Musuloju, Siddartha [AG63426] | PV38761 ClaimXten Expansion | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 8 | 8 | 0 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 |  | 4.5 | 2.5 |  |  |  | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  | 1
Naga, Tirumani Lakshmi [AG60852] | Cotiviti E & M Leveling | October 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 500 | 0 |  |  |  |  | 700 | 0 | [6 empty] | 240 | 0 | [8 empty] | 80 | 0 |  |  |  | 80 | 0 |  |  |  | 40 | 0 |  |  |  | 110 | 0
Naga, Tirumani Lakshmi [AG60852] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 60.5 | -60.5 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 | 60.5 | [5 empty] | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Naga, Tirumani Lakshmi [AG60852] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 184 | 99.5 | 84.5 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 81.5 | [5 empty] | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 18
Naga, Tirumani Lakshmi [AG60852] | Others |  | Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 16 | [20 empty] | 16 | Due to health issues took leave - [8.00];Took emergency leave due to the demise of my uncle - [8.00]
Naga, Tirumani Lakshmi [AG60852] | PV38761 ClaimXten Expansion | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Nalluri, Baji babu [AG67786] | Cotiviti Expansion July Release | July 2020 | Tech Lead | Ghosh, Ayan | Saxon Joseph | Waterfall | 80 | 85 | -5 | 110 | 0 |  |  | 150 | 0 |  | 3 | 5 | 9 | 350 | 0 | 18 | 7.5 | 10.5 | 15 |  |  | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  | 17
Nalluri, Baji babu [AG67786] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Tech Lead | Ghosh, Ayan | Saxon Joseph | Waterfall | 104 | 110.5 | -6.5 | 400 | 0 |  |  | 1000 | 0 |  | 3.5 |  | 5 | 1500 | 0 | 13.5 | 18 | 24.5 | 20.5 |  | 4 | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 21.5
Nalluri, Baji babu [AG67786] | PV36064 Cotiviti Pre to Post Phase 3 | June 2020 | Tech Lead | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 230 | 0 | [6 empty] | 150 | 386 | [8 empty] | 150 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 62 | 0
Nalluri, Baji babu [AG67786] | PV38761 ClaimXten Expansion | June 2020 | Tech Lead | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0
Pradhan, Jyotirekha [AG18454] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 60 | 9 | 51 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 | [6 empty] | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  | 9 |  | 50 | 0
Pradhan, Jyotirekha [AG18454] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 124 | 163 | -39 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 38.5 | 37.5 |  | 7 | 10 | 2 | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 68
Pradhan, Jyotirekha [AG18454] | Others |  | Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 32 | [20 empty] | 32 | i was on sick leave - [8.00];I was having fever - [16.00];It was holiday - [8.00]
Pradhan, Jyotirekha [AG18454] | PV36064 Cotiviti Pre to Post Phase 3 | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 230 | 0 | [6 empty] | 150 | 386 | [8 empty] | 150 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 62 | 0
Pradhan, Jyotirekha [AG18454] | PV36064_Cotiviti expansion | February 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 0 | 0 | 0
Reddy, Madhan [AG61751] | Cotiviti Expansion July Release | July 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 100 | 80.7 | 19.3 | 110 | 0 |  |  | 150 | 0 |  |  |  |  | 350 | 0 |  |  |  |  | 23.2 |  | 80 | 0 | [8 empty] | 80 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 | 30 |  | 4 | 50 | 0 |  |  | 23.5
Reddy, Madhan [AG61751] | Cotiviti Online & Adjustments Phase 1- Sep | September 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 64 | 96.5 | -32.5 | 400 | 0 |  |  | 1000 | 0 |  |  |  |  | 1500 | 0 | 18 | 47.7 |  | 5 |  |  | 250 | 0 | [8 empty] | 120 | 0 |  |  |  | 70 | 0 |  |  |  | 80 | 0 |  |  |  | 80 | 0 |  |  | 25.8
Reddy, Madhan [AG61751] | Others |  | Software Engineer | Ghosh, Ayan | Saxon Joseph | [54 empty] | 8 | [20 empty] | 8 | Sick leave - [8.00]
Reddy, Madhan [AG61751] | PV38761 ClaimXten Expansion | June 2020 | Software Engineer | Ghosh, Ayan | Saxon Joseph | Waterfall | 20 | 0 | 20 | 200 | 0 |  |  | 390 | 0 |  |  |  |  | 950 | 0 | [6 empty] | 50 | 438 | [8 empty] | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0 |  |  |  | 50 | 0